## Fee Title Acquisition Implementation Schedule

| Activities | Targeted Completion/Delivery Date | Responsible Party | Completion Date | Notes |
| --- | --- | --- | --- | --- |
| Hypothetical Agricultural Conservation Easement/Covenants and Restrictions/Grant Deed (6 months from Initial GA) |  |  |  |  |
| First draft to Department for review |  | Grantee |  | ACE will not be recorded, SALC R10 CE template required |
| First exhibit drafts to Department for review |  | Grantee |  |  |
| Department approval of draft agricultural conservation easement(s)/covenants and restrictions (+6 months) |  | DOC |  |  |
| Department approval of exhibits (+6 months) |  | DOC |  |  |
| Form of Irrevocable Offer to Convey (OTC) & Form of Notice of Unrecorded Grant Agreement (NUGA) (6 months from Initial GA) |  |  |  |  |
| Draft submitted or prepared by GM |  | DOC |  |  |
| Final, signature-ready version of OTD approved by GM (+ 6 months from submittal) |  |  |  |  |
| Final, signature-ready version of NUGA approved by GM (+ 6 months from submittal) |  |  |  |  |
| Title – Reports/Subordinations/Updated PTR (ongoing) |  |  |  |  |
| [Mineral remoteness evaluation to Department for review and approval] |  | Grantee |  | Only required if mineral rights are separated. |
| [Department approval of mineral remoteness evaluation] |  | DOC |  |  |
| [Phase One ESA to Department for review and approval] |  | Grantee |  |  |
| [Department approval of Phase One ESA] |  | DOC |  |  |
| Updated PTR and PTR Review Sheet to Department for Review |  | Grantee |  | PTR updated every 12 months, and/or at significant events (e.g. seller conveys new easement or lease during transaction) |
| Department approval of updated PTR and PTR Review Sheet |  | DOC |  |  |
| Appraisal (4.5 months) |  |  |  |  |
| Appraisal submitted to Department for review |  | Grantee |  | Must contain DOC-approved ACE and updated PTR |
| Appraisal reviewed and approved by Department (+2-3 weeks) |  | DOC |  |  |
| Appraisal submitted to DGS for review and approval (+1 week) |  | DOC |  |  |
| Appraisal approved by DGS (+1 month) |  | DGS |  |  |
| Grant Agreement Amendment to include Hypo ACE, additional terms and conditions, and Forms of OTC/NUGA Docs (1 year from Initial GA) |  |  |  |  |
| Draft Grant Agreement to Grantee |  | DOC |  |  |
| Grantee submit proposed edits to DOC |  | Grantee |  |  |
| Execute Grant Agreement (+ 2 months) |  | DOC |  |  |
| Baseline Documentation Report (6 weeks) |  |  |  |  |
| First Baseline Documentation Report draft to Department for review |  | Grantee |  | Use SALC BDR Checklist as a reference |
| Department approval of Baseline Documentation Report (+6 weeks) |  | DOC |  |  |
| Management Plan / Carbon Farm Plan (if applicable) |  |  |  |  |
| First [Management Plan/Carbon Farm Plan] draft to Department for review |  | Grantee |  |  |
| Department approval of [Management Plan/Carbon Farm Plan] |  | DOC |  |  |
| CLOSING DOCUMENTS (4 to 8 weeks) |  |  |  |  |
| Pro Forma (2 weeks) |  |  |  |  |
| Proforma to Department for review (after DOC approval of Updated PTR and PTR Review Sheet) |  | Grantee |  |  |
| Department approval of Proforma |  | DOC |  |  |
| Grant Deed (signature-ready pdf) |  |  |  |  |
| NUGA (signature-ready pdf) |  |  |  |  |
| OTC (signature-ready pdf) |  |  |  |  |
| Escrow Instructions (3 weeks) |  |  |  |  |
| Submittal of draft joint escrow instructions to Department |  | Grantee |  |  |
| Department review and approval of draft escrow instructions (+1 week) |  | DOC |  |  |
| Circulate approved escrow instructions for signatures (+2 weeks) |  | Grantee |  |  |
| Estimated Escrow Closing Statement |  |  |  |  |
| Submittal of estimated escrow closing statement to Department |  | Grantee |  |  |
| Acquisition Invoice/Warrant (6 weeks) |  |  |  |  |
| Draft invoice to Department for review |  | Grantee |  |  |
| Final invoice to Department (+3 weeks) |  | Grantee |  |  |
| Department Submittal of Invoice for Payment (+1 week) |  | DOC |  |  |
| Warrant received by Department (+2 weeks) |  | DOC |  |  |
| Department warrant delivered into escrow (+1 week) |  | DOC |  |  |
| Escrow Closing Date |  |  |  |  |
| POST-CLOSING DOCUMENTS |  |  |  |  |
| Submission of project documents post-closing (+4 weeks) |  |  |  |  |
| Copy of recorded easement(s) and Subordination Agreements to Department |  | Grantee |  |  |
| Copy of Title Insurance Policy submitted to Department |  | Grantee |  |  |
| Escrow closing statement submitted to Department |  | Grantee |  |  |
| Final Baseline Documentation Report submitted to Department |  | Grantee |  |  |
| Final Report submitted to Department |  | Grantee |  |  |
| Copy of Recorded Grant Deed |  |  |  |  |
| Copy of Recorded OTC |  |  |  |  |
| Copy of Recorded NUGA |  |  |  |  |
| Associated Costs Invoice (7 weeks) |  |  |  |  |
| Submittal of Draft Associated Costs Invoice to Department |  | Grantee |  |  |
| Submittal of Final Associated Costs Invoice to Department (+2 weeks) |  |  |  |  |
| Department Submittal of Invoice for Payment (+1 week) |  | DOC |  |  |
| Warrant issued and mailed to Grantee (4 weeks) |  | DOC |  |  |
| Grant Term End Date |  |  |  |  |